## Gantt Chart
BABYFUND THAILAND ¦ CASE STUDY
Family Savings Coordination Platform
PROJECT PLAN — GANTT CHART
Illustrative overlapping activity windows only; gate timing and critical path are not validated.
Edition | Portfolio edition
Start | 03 August 2026
Duration | 14 four-week blocks (56 weeks), not 14 calendar months
Author | Tankhun Luengchaicharn, Junior IT Business Analyst
Task ID | Task Name | Phase | Owner | Start Date | End Date | Duration (wks) | Related task(s) | Status | B1 Aug 26 | B2 Aug 26 | B3 Sep 26 | B4 Oct 26 | B5 Nov 26 | B6 Dec 26 | B7 Jan 27 | B8 Feb 27 | B9 Mar 27 | B10 Apr 27 | B11 May 27 | B12 Jun 27 | B13 Jul 27 | B14 Aug 27
1. Discovery & Regulatory
T01 | Stakeholder interviews & requirements gathering | Discovery & Regulatory | Business Analyst | 2026-08-03 | 2026-08-23 | 3 |  | Not Started
T02 | Competitive & market research | Discovery & Regulatory | Business Analyst | 2026-08-03 | 2026-08-30 | 4 |  | Not Started
T03 | Identify & shortlist candidate broker partners | Discovery & Regulatory | Product Manager | 2026-08-10 | 2026-09-13 | 5 |  | Not Started
T04 | Broker partnership negotiation | Discovery & Regulatory | CEO / Product Manager | 2026-09-07 | 2026-11-22 | 11 | T03 | Not Started
T05 | Legal review of ownership, funding rights and withdrawal terms | Discovery & Regulatory | Legal Counsel | 2026-08-31 | 2026-10-11 | 6 | T01 | Not Started
T06 | PDPA & AML compliance framework design | Discovery & Regulatory | Compliance Officer | 2026-08-31 | 2026-10-25 | 8 | T01 | Not Started
T07 | Conditional partner feasibility and terms gate | Discovery & Regulatory | CEO | 2026-10-26 | 2026-11-08 | 2 | T04 | Not Started
T08 | Finalize BRD & FRD sign-off | Discovery & Regulatory | Business Analyst | 2026-10-12 | 2026-11-08 | 4 | T05,T06 | Not Started
2. Design
T09 | UX research & wireframes | Design | UI/UX Designer | 2026-11-02 | 2026-12-06 | 5 | T08 | Not Started
T10 | System architecture & API planning with broker | Design | IT Development Team | 2026-11-09 | 2026-12-13 | 5 | T07 | Not Started
T11 | Visual design & prototyping | Design | UI/UX Designer | 2026-11-23 | 2026-12-20 | 4 | T09 | Not Started
T12 | Design sign-off | Design | Product Manager | 2026-12-21 | 2026-12-27 | 1 | T10,T11 | Not Started
3. Development Sprint 1
T13 | KYC & onboarding module | Development Sprint 1 | IT Development Team | 2026-12-21 | 2027-01-31 | 6 | T12 | Not Started
T14 | Child profile, age gate and proposed partner account reference | Development Sprint 1 | IT Development Team | 2026-12-28 | 2027-02-07 | 6 | T12 | Not Started
T15 | Provider-approved payment route feasibility and mock states | Development Sprint 1 | IT Development Team | 2027-01-18 | 2027-02-28 | 6 | T12 | Not Started
T16 | Private invite, unpaid intent and guardian review flow | Development Sprint 1 | IT Development Team | 2027-02-01 | 2027-03-14 | 6 | T14 | Not Started
T17 | Alpha build & internal testing | Development Sprint 1 | IT Development Team / QA | 2027-03-15 | 2027-04-11 | 4 | T13,T14,T15,T16 | Not Started
4. Development Sprint 2
T18 | Family Fund Circle & Merit Contribution | Development Sprint 2 | IT Development Team | 2027-03-15 | 2027-04-25 | 6 | T16 | Not Started
T19 | Pooled goals and scenario projector | Development Sprint 2 | IT Development Team | 2027-03-22 | 2027-04-25 | 5 | T14 | Not Started
T20 | S&P 500 vehicle feasibility (partner dependent) | Development Sprint 2 | IT Development Team | 2027-03-29 | 2027-05-02 | 5 | T07 | Not Started
T21 | LINE integration (login, notifications, backup channels) | Development Sprint 2 | IT Development Team | 2027-04-12 | 2027-05-09 | 4 | T13 | Not Started
T22 | BabyFund Academy content & module | Development Sprint 2 | Marketing Team | 2027-04-12 | 2027-05-16 | 5 | T12 | Not Started
T23 | Beta build | Development Sprint 2 | IT Development Team | 2027-05-10 | 2027-05-23 | 2 | T18,T19,T20,T21,T22 | Not Started
5. Testing & UAT
T24 | QA functional testing | Testing & UAT | QA Team | 2027-05-17 | 2027-06-20 | 5 | T23 | Not Started
T25 | Compliance & regulatory review with broker partner | Testing & UAT | Compliance Officer | 2027-05-24 | 2027-06-27 | 5 | T23 | Not Started
T26 | Proposed parent-user UAT (not executed) | Testing & UAT | Business Analyst / Product Manager | 2027-06-07 | 2027-07-04 | 4 | T24 | Not Started
T27 | Bug fixes & final adjustments | Testing & UAT | IT Development Team | 2027-06-21 | 2027-07-18 | 4 | T24,T26 | Not Started
T28 | UAT sign-off | Testing & UAT | Product Manager | 2027-07-12 | 2027-07-25 | 2 | T27 | Not Started
6. Launch
T29 | App Store & Google Play submission | Launch | IT Development Team | 2027-07-19 | 2027-08-08 | 3 | T28 | Not Started
T30 | Marketing launch campaign preparation | Launch | Marketing Team | 2027-07-05 | 2027-08-08 | 5 | T25 | Not Started
T31 | Customer support readiness training | Launch | Customer Support Lead | 2027-07-19 | 2027-08-08 | 3 | T28 | Not Started
T32 | Go live & onboard first accounts | Launch | CEO / Product Manager | 2027-08-09 | 2027-08-29 | 3 | T29,T30,T31 | Not Started
MILESTONES
MS-1 | Proposed partner and payment feasibility gate (not signed) |  |  | 2026-11-08 | Ref: T07 |  |  | Planned |  |  |  | ◆
MS-2 | Design Sign-off |  |  | 2026-12-27 | Ref: T12 |  |  | Planned | [5 empty] | ◆
MS-3 | Alpha Build Complete |  |  | 2027-04-11 | Ref: T17 |  |  | Planned | [8 empty] | ◆
MS-4 | Beta Build Complete |  |  | 2027-05-23 | Ref: T23 |  |  | Planned | [10 empty] | ◆
MS-5 | UAT Sign-off |  |  | 2027-07-25 | Ref: T28 |  |  | Planned | [12 empty] | ◆
MS-6 | Go Live |  |  | 2027-08-29 | Ref: T32 |  |  | Planned | [13 empty] | ◆
Total Tasks | 32 | Total Milestones | 6
Project Start | 2026-08-03 | Project End (Go Live) | 2027-08-29

## Notes & Legend
Notes & Phase Legend
Timeline basis | Each B column is a four-week planning block from 3 Aug 2026, not a calendar month. B1 and B2 both display Aug 2026. Dates are illustrative and unapproved.
Corrected timeline | Illustrative 14-block launch scenario only; no partner agreement, build, UAT or launch occurred. Partner role, product, payer route and withdrawal policy are stop/go gates, not completed milestones.
Phase Color Legend
1. Discovery & Regulatory
2. Design
3. Development Sprint 1
4. Development Sprint 2
5. Testing & UAT
6. Launch
Milestone marker | A navy diamond (◆) marks the illustrative four-week block of each milestone.
Dependencies | Column H lists related inputs, not finish-to-start dependencies. Several activities overlap. This is not a validated critical path or an executable launch commitment; partner, payment, ownership, suitability and legal gates must be sequenced anew before any real plan.